## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 230 | 0 | 230 |  |  | 47 | 2 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3
| 2016-12-16 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-11-04 | 2016-11-07 | 2016-11-11 | 2016-11-14 | 2016-11-18 | 2016-11-21 | 2016-11-25 | 2016-11-28 | 2016-12-02 | 2016-12-05 | 2016-12-09 | 2016-12-12 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
7 | [25 empty] | Verify?
62 |  | Player
63 | 1 | Movement | TB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 1 | Face Direction | TB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 1 | Pickup Balls | TB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 1 | Throw Balls | TB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 1 | Charge Throw Balls | TB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 2 | Charge Bar | TB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Damage | NS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Punch | TB |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | I Frames | ALL |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Steal point for catch | NA |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Dropped Idea
70 |  | Player Controls
71 | 1 | Controller Script | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | Movement Joystick | KC |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 1 | Direction Joystick | KC |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 1 | Triggers | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Vibration from charging | KC |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Dropped idea
| 1 | Dashing | NA |  | 3 |  | 1 |  | 3 | 2016-10-26: 3; 2016-10-28: 3; 2016-10-31: 0
| 1 | Freeze players on starting level | NA |  | 1 |  | 1 |  | 1 | 2016-10-26: 1; 2016-10-28: 1; 2016-10-31: 0; 2016-11-07: 0
| 1 | Charging balls goes up and down | TB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Gradual increase in speed after being stunned (in daze) | ALL |  | 4 | 0 | 1 |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Push to deflect balls | TB |  | 2 |  | 1 |  | 2 | 2016-10-26: 2; 2016-10-28: 2; 2016-10-31: 2
| 1 | Fly back on hit | NA |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 |  | Player Art
76 | 2 | Coloring | NS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 4 | Modelling | TB |  | 4 | 0 | 4 |  | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 4 | Rigging | TB |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 4 | Animation | TB |  | 6 | 0 | 6 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 4 | Animation Controller | TB |  | 5 | 0 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 4 | Materials | TB |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82
83 |  | Ball
84 | 1 | Trajectory | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 1 | Bounciness | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 1 | Friction | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 1 | Ball "Heat" (Damage) | TB |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 2 | Trail | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 2 | Glow near player | TB |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 1 | Source (Person who threw ball) | KC |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 4 | Squash and Stretch | KC | NS | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
92 | 4 | Model / Texture | TB |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Aim Assist | KC |  | 3 | 0 | 1 |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | C-C-C-C-COMBO BALL | ALL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Throw two balls at the same time | NA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95
93 |  | Special Balls
94 | 2 | Fast | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 4 | Model: Hot Coal | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 2 | Bouncy | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 4 | Model: Horse Shoe | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 3 | Boomerang | NS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
98 | 4 | Model: Boomerang | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
99 | 3 | Uncatchable | KC |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 4 | Model: Cactus Fruit | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 3 | Tron | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 4 | Model: Manure | TB |  | 1 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 3 | Ghost | NA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 4 | Model: Ghosty Skull | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Reported
108 | 3 | Slow Grow | NA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
109 | 4 | Model: balloon | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Reported
108 | 3 | Homing (Accelerats towards players) | NA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
109 | 4 | Model: Bool | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Reported
108 | 3 | Combo (Bounces towards players) | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
109 | 4 | Model: Sherrif's Star | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
93 |  | Powerups
112 | 2 | Increase movement speed temporarily | TB |  | 2 | 0 |  |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | Reported
113 | 4 | Model: Green Bottle | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
114 | 2 | Increase grab range temporarily | TB |  | 2 | 0 |  |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | dropped idea | Reported
115 | 4 | Model: Lasso | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | dropped idea | Reported
116 | 3 | Drunk; Max charge | NA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
117 | 4 | Model: Red Bottle | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
118 | 3 | Invincibility, reflect back to player who threw it | NA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
119 | 4 | Model: Blue Bottle | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | Reported
Reported
Reported
93 |  | Game Managers
124 | 2 | Score System | NS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
125 | 3 | UI | NS |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
| 2 | Show crown over leader | ALL |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
126 | 2 | Time System | NS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
127 | 3 | UI | NS |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
128 | 2 | Player System | NS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
129 | 3 | UI | NS |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
130 | 4 | Audio Manager | KC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  | Reported
130 | 4 | Powerup Manager | NA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 |  | Stages
132 | 2 | Stage 1 Protototyping - Cliffside | TB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
133 | 4 | Asset Creation | TB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | Reported
134 | 4 | Building | KC |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
135 | 3 | Stage 2 Prototyping - Town | KC |  | 4 | 0 | 1 |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
136 | 4 | Asset Creation | TB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | Reported
137 | 4 | Building | KC |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
138 | 3 | Stage 3 Prototyping - Train Station | KC |  | 4 | 0 | 1 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | Reported
139 | 4 | Asset Creation | TB |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | Reported
140 | 4 | Building | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  | Reported
138 | 3 | End Game Scene | NA |  | 4 | 0 | 1 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
142
143
144
145
146
147 | [25 empty] | Reported
93 |  | Out-Of-Game Things
149 | 3 | Player Ready/Customization Screen | NS |  | 5 | 0 | 5 |  | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
150 | 3 | Stage Select Screen | NS |  | 5 | 0 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | Reported
151 | 4 | Score Screen | NA |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
| 2 | Round Handling | NS |  | 4 | 0 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
152 | 3 | Tutorial Scene | NS |  | 8 | 0 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 1 | 0 | 0 | 0 | 0 |  | Reported
| 1 | Show score, +1 or -1, over players heads during play | NA |  | 3 | 0 | 1 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
| 1 | Camera automatic adjustment | KC |  | 4 | 0 | 2 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 60 FPS | TB |  | 3 | 0 | 1 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Scene Transitions | KC |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| 3 | Train Smoke | NA |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| 3 | Fireworks | NA |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
93 |  | Sound
155 | 4 | Menu Music | NS |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  | Reported
156 | 4 | In Game Music | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  | Reported
157 | 4 | Player Sounds (Throw Ball) | KC |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  | Reported
158 | 4 | Ball Sounds (Hit wall, Hit Player) | KC |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  | Reported
159 | 4 | PowerUp Sounds | KC |  | 3 | 0 | 1 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 |  | Reported
159 | 4 | Environment Sounds | KC |  | 3 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 |  | Reported
160 | 4 | Menu Sounds | KC |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 |  | Reported
162 | [25 empty] | Reported
163 |  | UI
160 | 1 | Bar show score and timer | NS |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
165 | 1 | Show post game score | NA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | Reported
166 | 1 | Flash timer with 10 seconds to go | NA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 47 | 47 | 45 | 42 | 38 | 35 | 31 | 28 | 24 | 21 | 17 | 14 | 10 | 7 | 3 | 0
211 |  | Optimum | [5 empty] | Line | 230 | 230 | 220.2128 | 205.5319 | 185.9574 | 171.2766 | 151.7021 | 137.0213 | 117.4468 | 102.766 | 83.1915 | 68.5106 | 48.9362 | 34.2553 | 14.6809 | 0
212
213 |  | Sum | [6 empty] | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229 | 229
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 51 | 51 | 51 | 34 | 16 | 16 | 10 | 10 | 8 | 2 | 2 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 34 | 34 | 34 | 25 | 14 | 14 | 11 | 10 | 9 | 9 | 9 | 9 | 6 | 5 | 3 | 0
217 |  |  | 3 | [5 empty] | 64 | 64 | 64 | 62 | 51 | 47 | 34 | 30 | 23 | 21 | 15 | 14 | 3 | 3 | 0 | 0
218 |  |  | 4 | [5 empty] | 78 | 78 | 78 | 78 | 76 | 66 | 57 | 48 | 40 | 36 | 35 | 35 | 17 | 10 | 2 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Nic Axeheim | NA |  |  |  |  | NA | 38 | 38 | 38 | 34 | 32 | 32 | 24 | 20 | 17 | 13 | 8 | 6 | 2 | 2 | 0 | 0
223 |  | Thomas Bartlet | TB |  |  |  |  | TB | 82 | 82 | 82 | 60 | 49 | 39 | 35 | 25 | 20 | 17 | 17 | 17 | 9 | 3 | 3 | 0
224 |  | Kyle Cooley | KC |  |  |  |  | KC | 56 | 56 | 56 | 54 | 46 | 45 | 30 | 30 | 28 | 25 | 25 | 25 | 13 | 11 | 0 | 0
225 |  | Nathan Stanifer | NS |  |  |  |  | NS | 43 | 43 | 43 | 43 | 26 | 23 | 21 | 21 | 13 | 11 | 9 | 8 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 10 | 10 | 10 | 10 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230
236

## Daily Scrum
Producer | 2016-12-16 |  | Team Members
Approved | Dates |  | Nic Axeheim | Thomas Bartlet | Kyle Cooley | Nathan Stanifer | All
| 2016-10-26 | Wed | NA | NA | NA | NA | Decided on team, came up with interesting game idea we would like to pursue.
| 2016-10-27 | Thu | NA | NA | NA | NA | NA
| 2016-10-28 | Fri | NA | NA | NA | NA | NA
| 2016-10-29 | Sat | NA | NA | NA | NA | NA
| 2016-10-30 | Sun | NA | NA | NA | NA | NA
| 2016-10-31 | Mon | NA | NA | NA | NA | NA
| 2016-11-01 | Tue | NA | NA | NA | NA | NA
| 2016-11-02 | Wed | NA | Done: Some prototyping Next: Make level bigger, basic spawn system | NA | NA | Met to talk about our game. Agreed on rules and game mechanics, general theme of the game and other details we would like to implement. Divided work amongst the team moving forward.
| 2016-11-03 | Thu | NA | NA | NA | NA | NA
| 2016-11-04 | Fri | NA | NA | Done: All controller input Next: Wait for feedback | NA | NA
| 2016-11-05 | Sat | Done: Worked on some special balls. Next: Decide on powerups. | Done: Punch, Daze | NA | NA | NA
| 2016-11-06 | Sun | NA | Done: Made Level Bigger, basic spawn system Next: Character Models | NA | NA | NA
| 2016-11-07 | Mon | Done: Started work on powerups manager. Finished homing ball, growing ball, ghost ball. Next:Talk to group what is needed right now. | Done:Modelled Character Next:Color Charachter | Done: Got feedback Next: Rumble controllers, fix frame-dependent movement
| 2016-11-08 | Tue | NA | N/A | Done: Started rumble controllers, got ball mostly squishing Next: Finish ball squishing, maybe do a special ball Help: Get ball squishing to local coordinates | Done: Started Main Menu Next: new color textures for players
| 2016-11-09 | Wed | Done: Finished powerup manager, specific powerups. Next: More Powerups. | Done: Color Character, Started Animations Next: More animations | Done: Uncatchable ball, combo ball, aim assist Next: Finish ball squishing, design cliffside stage Help: Get ball squishing to local coordinates | Done: New textures Next: Color select screen
| 2016-11-10 | Thu | NA |  | Done: Nothing Next: Finish ball squishing, design cliffside stage Help: Get ball squishing to local coordinates | Done: Color select screen Next: Start ball boomerang
| 2016-11-11 | Fri | Done: Finshed QuickThrow powerup, QuickCharge Powerup, and updated player so that powerups can be picked up. Next: Work on dashing. |  | Done: Cliffside stage Next: Finish ball squishing Help: Get ball squishing to local coordinates | Done: NA Next: NA
| 2016-11-12 | Sat | NA |  |  | Done: Some math for boomerang Next: Finish main menu and color select
| 2016-11-13 | Sun | NA | Done: Animations |  | Done: Finish main menu Next: polish some things
| 2016-11-14 | Mon | Done: Started work on dashing Next: Finish dashing.
| 2016-11-15 | Tue | NA
| 2016-11-16 | Wed | Done: Finsihed dashing, and updated players so that they can't move during countdown. Next: Create a score popup system above each player. |  |  |  | Met and discussed changes, additions, and removals of various features
| 2016-11-17 | Thu | Done: Created score models to be displayed above players. Next: Implement shown score in scripts and game. | Done: Implemented Character Animations | Done: Some camera adjusting, mostly movement Next: Finish camera movement, do camera zoom Help: figure how tf to do that
| 2016-11-18 | Fri | NA |  | Done: camera adjusting is done, ball trail is done, town level is prototyped and built (without assets) Next: Controller input for color select screen Help:
| 2016-11-19 | Sat | NA
| 2016-11-20 | Sun | Done: Implemented all code needed to display score above player when hitting someone or getting hit. Next: Meet with team to decide on what is needed. | Done: Ball Modelling
| 2016-11-21 | Mon | Done: Next: work on juicy timer, implement throwing from both hands at once, and an end score display. | Done: Ball Coloring | Done: some of the controller input Next: more controller input, camera adjust bug, ball hotness bug Help: | Done: SomeTutorial Next: more Tutorial
| 2016-11-22 | Tue | Done: Implemented a flashing timer for the last 10 seconds. Next: both hands throw, end score display. | Done: Special Ball Modelling
| 2016-11-23 | Wed | NA | Done: Special Ball Coloring
| 2016-11-24 | Thu | NA |  | Done: controller input, camera adjust bug, ball hotness bug Next: Fix dashing direction weirdness Help: | Done: Tutorial, Level Select, Controls Screen Next: More polish in levels and tutorial
| 2016-11-25 | Fri | NA |  | Done: spawning of items Next: Help:
| 2016-11-26 | Sat | NA | Done: Powerup Modelling And Coloring
| 2016-11-27 | Sun | Done: first iteration end canvas which displays scores. Can throw from both hands now. Next: | Done: Powerup Icons
| 2016-11-28 | Mon | Done: Implemented a knockback when a player is hit by a ball. Next: work on improving end screen with score display. | Done: Daze Icons | Done: fuckall, fixed tutorial camera, made charging max out, made power up give max charge instead of quick throw Next: meet with music person Help: | Done:tutorial polish Next: meet with music person Help:
| 2016-11-29 | Tue | Done: Added a timeout to all powerups, and changed daze so that there's a gradual increase in speed for the player. Next: end scene. | Done: Leader Icons
| 2016-11-30 | Wed | NA |  | Done: met with music person, started train station level Next: continue train station level, fix cow Help: | Done: met with music person, ui changes Next: more tutorial and boomerang Help:
| 2016-12-01 | Thu | Done: First iteration of end scene, players stand on bars that rises according to score, winner has the tallest bar. Next: Make end scene more juicy. | Done: Icon Implementation | Done: fixed cow, train station design done, spawning most objects in town and train station Next: wind Help: | Done: some tutorial, boomerang Next: level select more Help:
| 2016-12-02 | Fri | Done: Fixed logic of ghostball, and added fireworks to the end scene. Next: Check with team what needs to be done with end scene. Help: End scene background. |  | Done: wind, loading new levels from level select Next: start some sound effects Help: | Done:level select Next: update more ui Help:
| 2016-12-03 | Sat | NA | Done: Town Art Assets | Done: lots of sound effects Next: music and more sound effects Help: | Done: more ui and polish Next: polish ui more, finish boomerang Help:
| 2016-12-04 | Sun | NA | Done: Train Station Art Assets | Done: music Next: menu sound effects Help: | NA
| 2016-12-05 | Mon | NA |  | Done: fixed camera zoom/movement bugs Next: menu sound effects Help: | NA
| 2016-12-06 | Tue | Done: Updated logic of growing bars so that instead of set height, they are now relatively tall to the winner, also fixed bug with updating scores. Next: |  | Done: menu sound effects, cactus in cliffside, scene transitions Next: Help: | Done: Ui changes with more polish Next: UI text better Help:
| 2016-12-07 | Wed | NA | Done: Made text Nicer (Black Background)
| 2016-12-08 | Thu | NA
| 2016-12-09 | Fri | Done: Updated end scene layout so that it matches the rest of the game. Next: Work on making smoke for the train.
| 2016-12-10 | Sat | NA
| 2016-12-11 | Sun | Done: added smoke to train | Done: Some work on the trailer
| 2016-12-12 | Mon | NA |  | Done: ball smacking, boomerang spawning, more scene transitions Next: end scene sound effects & gameplay music Help: | Done: better ui text and more descriptive level select Next: polish menu screens Help:
| 2016-12-13 | Tue | NA |  | Done: end scene sound effects, some music Next: finish gameplay music Help: | Done: menu screens ploish Next: finish menu polish Help:
| 2016-12-14 | Wed | NA |  | Done: some gameplay music, moved charge bar in front of icons, juiced up level select Next: finish gameplay music Help: | Done: added back funtionality in menu Next: menu music Help:
| 2016-12-15 | Thu | NA | Done: More text stuff | Done: gameplay music, new color palette, fixed some buggy balls Next: wait for things to break Help: | Done: menu music, fix bugs Next: wait for things to break Help:
| 2016-12-16 | Fri | Done: Updated end scene, fixed some bugs. |  |  | Done: menu music, fix bugs, hope nothing breaks